Evaluation and Appraisal Report Draft Local Planning Agency Schedule

| March 2015 | Discuss schedule, timing of possible workshops, general staff and member comments, identification of major issues, review of elements schedule, workshop schedule |
| --- | --- |
| April 2015 | Review Utilities Element, Stormwater Management Element, and Public Schools Element |
| May 2015 | Review Utilities Element, Stormwater Management Element, and Public Schools Element Review Vision Statement (Envisioning Tomorrows…), and Community Design Element |
| June 2015 | Review Coastal Management Element, Conservation Element, and Recreation Element |
| July 2015 | No hearing |
| August 2015 | Review Transportation Element |
| September 2015 | Review Future Land Use Element, and Housing Element |
| *October 2015 November 2015 | Review Historic Preservation Element, Intergovernmental Coordination Element (ICE), and Capital Improvements Element Review Procedures and Monitoring, mapping |
| January/February 2016 | Back up dates, report preparation |
| March 2016 | Back up dates, report preparation |
| April 2016 May 2016 | Draft Report Presentation, LPA Review LPA Review, & Recommendation |